## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Aanchal | Alper | Michael | Nikoloz | Od | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 0 |  | 0
|  | Design architecture | Architect | Michael
| Documentation |  |  |  |  | 34 |  | 0 | [5 empty] | 0
|  | Project Charter | Project Manager | Od | 2
|  | Release Plan | Project Manager | Nikoloz, Alper | 5
|  | Requirements Document | Project Manager, Requirements Engineer | Alper, Nikoloz, od | 6
|  | Project Plan | Project Manager, Developers | Od, Michael, Aanchal, Nikoloz, Alper | 5
|  | Test Plan | Tester | Aanchal, Nikoloz | 8
|  | User Guide & System Admin Doc | Developers, Requirments Engineer | Alper. Aanchal | 4
|  | Architecture Document | Architect | Michael, Aanchal | 4
Coding | [6 empty] | 0 | [6 empty] | 0
Iteration 1: | Development |  |  |  |  | 35 |  | 0 | [5 empty] | 0
|  | Research and learn new language/s and environment | Developer | All | 20 |  | 0 | [6 empty] | 0
|  | Setup Development Environment | Developer | Michael | 2 |  | 0 | [6 empty] | 0
|  | Install Language Requirments on Devices | Developer | All | 4 |  | 0 | [6 empty] | 0
|  | Learn Git/github | Developer | Aanchal, Nikoloz | 2 |  | 0 | [6 empty] | 0
|  | Plan Database Schema (ER diagrams) | Developer | Nikoloz, Aanchal | 5 |  | 0 | [6 empty] | 0
|  | Plan API Endpoints and Payloads | Developer | Michael, Aanchal | 2 |  | 0 | [6 empty] | 0
| Analysis |  |  |  |  | 4 |  | 0 | [5 empty] | 0
|  | System Testing | All | All | 4 |  | 0 | [6 empty] | 0
|  | Evaluate needs for next iteration | Project Manager | Od | 2 |  | 0 | [6 empty] | 0
Total |  |  |  |  | 75 | 73 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0