## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Aanchal | Alper | Michael | Nikoloz | Od | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 0 |  | 0
|  | Design architecture | Architect | Michael
| Documentation |  |  |  |  | 34 |  | 14 | [5 empty] | 0
|  | Project Charter | Project Manager | Od | 2 |  | 4 | [5 empty] | 4 | 4
|  | Release Plan | Project Manager | Nikoloz, Alper | 5 |  | 0
|  | Requirements Document | Project Manager, Requirements Engineer | Alper, Nikoloz, od | 6 |  | 10 |  | 2 | 2 | 2 | 2 | 2 | 10
|  | Project Plan | Project Manager, Developers | Od, Michael, Aanchal, Nikoloz, Alper | 5 |  | 0
|  | Test Plan | Tester | Aanchal, Nikoloz | 8 |  | 0
|  | User Guide & System Admin Doc | Developers, Requirments Engineer | Alper. Aanchal | 4 |  | 0
|  | Architecture Document | Architect | Michael, Aanchal | 4 |  | 0
Coding | [6 empty] | 0 | [6 empty] | 0
Iteration 1: | Development |  |  |  |  | 35 |  | 45 | [5 empty] | 0
|  | Research and learn new language/s and environment | Developer | All | 20 |  | 24 |  | 6 | 5 | 2 | 6 | 5 | 24
|  | Setup Development Environment | Developer | Michael | 2 |  | 1 |  |  |  | 1 |  |  | 1
|  | Install Language Requirments on Devices | Developer | All | 4 |  | 12 |  | 2 | 3 | 2 | 2 | 3 | 12
|  | Learn Git/github | Developer | Aanchal, Nikoloz | 2 |  | 2 |  | 1 |  |  | 1 |  | 2
|  | Plan Database Schema (ER diagrams) | Developer | Nikoloz, Aanchal | 5 |  | 2 |  | 1 |  |  | 1 |  | 2
|  | Plan API Endpoints and Payloads | Developer | Michael, Aanchal | 2 |  | 4 |  |  |  | 4 |  |  | 4
| Analysis |  |  |  |  | 4 |  | 9 | [5 empty] | 0
|  | System Testing | All | All | 4 |  | 4 |  | 1 | 1 | 1 | 1 | 1 | 5
|  | Evaluate needs for next iteration | Project Manager | Od | 2 |  | 5 |  |  |  | 5 |  |  | 5
Coding
Iteration 2: | Development |  |  |  |  | 56 |  | 15
|  | Create User Model (API) | Developer | Michael, Nikoloz | 4 |  | 5 |  |  |  | 4 | 1 |  | 5
|  | Create Session Model (API) | Developer | Michael, Alper | 6 |  | Roll Over |  |  | Roll Over | Roll Over
|  | Create Triggers Model (API) | Developer | Aanchal, Od | 8 |  | Roll Over |  | Roll Over |  |  |  | Roll Over
|  | Create Triggered Events Model (API) | Developer | Nikoloz, Alper | 8 |  | Roll Over |  |  | Roll Over |  | Roll Over
|  | Create Transaction Model (API) | Developer | Alper, Michael | 8 |  | Roll Over |  |  | Roll Over | Roll Over
|  | Create Account Model (API) | Developer | Od, Aanchal | 6 |  | Roll Over |  | Roll Over |  |  |  | Roll Over
|  | Create Prototype App (React) | Developer | Michael, Od | 8 |  | Roll Over |  |  |  | Roll Over |  | Roll Over
|  | Environment Compatibility | Developer | All | 8 |  | 10 |  | 2 | 2 | 2 | 2 | 2 | 10
| Analysis |  |  |  |  | 12 |  | 17
|  | Create Design For UI | Developer | Od, Nikoloz | 4 |  | 6 |  |  |  |  | 1 | 5 | 6
|  | Evaluate Needs for Next Iteration | Developer | Aanchal, Michael | 4 |  | 5 |  | 2.5 |  | 2.5 |  |  | 5
|  | Evaluate Security Needs | Developer | Alper, Aanchal | 4 |  | 6 |  | 2 | 4 |  |  |  | 6
| Misc. |  |  |  |  | 0 |  | 0
|  | Closeout tasks | Developer | Nikoloz | 2 |  | 2 |  |  |  |  | 2 |  | 2
Coding
Iteration 3: | Development |  |  |  |  | 48 |  | 41
|  | Create User Model (API) | Developer | Michael, Nikoloz | 4 |  | 4 |  |  |  | 4 |  |  | 4
|  | Create Session Model (API) | Developer | Michael, Alper | 6 |  | 4 |  |  |  | 4 |  |  | 4
|  | Create Triggers Model (API) | Developer | Aanchal, Od | 8 |  | 4 |  | 4 |  |  |  |  | 4
|  | Create Triggered Events Model (API) | Developer | Nikoloz, Alper | 8 |  | 9 |  |  |  |  | 9 |  | 9
|  | Create Transaction Model (API) | Developer | Alper, Michael | 8 |  | 10 |  |  | 10 |  |  |  | 10
|  | Create Account Model (API) | Developer | Od, Aanchal | 6 |  | 10 | [5 empty] | 10 | 10
|  | Create Prototype App (React) | Developer | Michael, Od | 8 |  | 0 | [6 empty] | 0
| Analysis | [6 empty] | 6
|  | Evaluate Needs for Next Iteration | Developer | Aanchal, Michael | 4 |  | 6 |  | 2
| Misc. |  |  |  |  | 0 |  | 0
|  | Closeout tasks | Developer | Aanchal | 2 |  |  |  | 2
Coding
Iteration 4 | Development | [6 empty] | 40
|  | add route for exporting transactions as csv | Developer | Michael | 2 |  | 0 |  |  |  | Roll Over
|  | add interactions between transactions and bank account | Developer | Alper | 15 |  | 8 |  |  | 8
|  | add interactions between transactions and transactions triggers | Developer | Aanchal | 15 |  | 2 |  | 1 |  | 1
|  | add interactions between triggered Event and Notifications | Developer | Nikoloz | 15 |  | 8 |  |  |  |  | 8
|  | add ability to add custom categories to transactions | Developer | Michael | 2 |  | 3 |  |  |  | 3
|  | add ability to nullify a session | Developer | Michael | 5 |  | 0 |  |  |  | Dropped
|  | Begin setting up UI | Developer | Michael | 10 |  | 4 |  |  |  | 4
|  | Add Login Page | Developer | Michael | 5 |  | 0 |  |  |  | Roll over
|  | Add Trigger Sub Types | Developer | Aanchal | 10 |  | 6 |  | 4 |  | 2
|  | Add Notification Model | Developer | Michael | 3 |  | 3 |  |  |  | 3
|  | Add better validations to accounts | Developer | Od | 10 |  | 6 |  |  |  | 3 |  | 3
Coding
Iteration 5 | Development
|  | add route for exporting transactions as csv | Developer | Michael | 1 |  | 3 |  |  |  | 3
|  | Create login and sign up page | Developer | Michael | 4 |  | 5 |  |  |  | 5
|  | Revamp authorization (optional) | Developer | Michael | 2 |  | 0 |  |  |  | ROLL OVER
|  | Create Navigation | Developer | Michael | 4 |  | 4 |  |  |  | 4
|  | Create User Profile page | Developer | Michael | 4 |  | 8 |  |  |  | 8
|  | Create Acounts page | Developer | Aanchal | 8 |  | 13 |  | 10 |  | 3
|  | Create Dashboard page | Developer | Od | 8 |  | 13 |  |  |  | 3 |  | 10
|  | Create initial base ui app | Developer | Michael | 4 |  | 2 |  |  |  | 2
|  | add a notifications view/panel | Developer | Alper | 8 |  | 5 |  |  |  | 5
|  | Create a page for viewing triggers that were set off | Developer | Nikoloz | 8 |  | 0 |  |  |  | ROLL OVER
|  | Update unit tests for Accounts | Developer | Od | 3 |  | 6 |  |  |  | 2 |  | 4
|  | Update unit tests for transactions | Developer | Alper | 3 |  | 4 |  |  | 4
|  | Update unit tests for Triggers | Developer | Aanchal | 3 |  | 4 |  | 4
|  | Update unit tests for Users | Developer | Michael | 3 |  | 2 |  |  |  | 2
|  | Update unit tests for Triggered Events | Developer | Nikoloz | 3 |  | 0
Total |  |  |  |  | 357 | 189 | 258 | 187 | 46.5 | 39 | 86.5 | 36 | 49 | 257